## Sheet1
Issue | How it could have been prevented? | How to address this issue?
Identifying exact Sponsor | Discuss who the sponsor can be with the professor. Understand scope of panel members. | Get Project Charter reviewed by the professor.
Incorrect and missing stakeholders | Thorough analysis of the problem statement and scope of the project. | Get Stakeholders reviewed by the professor.
Incorrect direction of requirements | Understanding scope of requirements document thoroughly. | Get Requirements document reviewed by the professor.
Missing elements on the Work Breakdown Structure | Thorough analysis of the problem statement and scope of the project. | Get WBS reviewed by the professor.
Misunderstanding scope of panel | Request clarification from the professor. | Connect with the professor.
Delayed progress | Include sufficient buffer time, follow up with team members and proactively meet every week to make progress. | Rework schedule of the project.
Not scheduling/anticipating sufficient time for requirements document | Include sufficient buffer time, follow up with team members and proactively meet every week to make progress. | Rework schedule of the project.
Not understanding the "what" of communication plan | Understanding scope of communications plan document thoroughly. | Connect with the professor.
Overestimating cost of the project | Research more on costs involved in completing the project. | Get cost estimate reviewed by the professor.
Unable to clearly specify authorities in Project Charter | Clearly understand authorities with respect to responsibilities. | Get Project Charter reviewed by the professor.
Unable to decide topic of non-profit | Thorough analysis of the problem statement and scope of the project. More research on topics. | Gain better understanding and research ideas from the internet.
Unavailability of getting all team members together | Fixing a pre-determined time slot every week that works for all the team members. | Meet virtually during late hours/weekends or after weekly class.
Understanding the scope of project | Thorough analysis of the problem statement and scope of the project. | Connect with the professor.